## Gantt chart project plan PROGRE
Phase Name | Activity | Start Date | Duration in days | End Date | Duration in weeks
First Submission | Project Contract | 2018-10-01 | 20 | 2018-10-21 | 3
Ethical Forms
Project Plan
Global Checklist and BCS Checklist
| BCS Checklist | 2018-10-01 | 20 | 2018-10-21 | 3
Second Submission | Graphical User Interface feature | 2018-10-22 | 14 | 2018-11-05 | 2
Requirements Specification
Documentation design
| Create, log in or remove account FEATURE | 2018-11-04 | 7 | 2018-11-11 | 1
Testing
Documentation
| Researching and preparing recipes | 2018-11-12 | 7 | 2018-11-19 | 1
Designing how recipes are going to be selected
| Creating JSON file containing recipes | 2018-11-12 | 14 | 2018-11-26 | 2
| User inputs FEATURE | 2018-11-26 | 14 | 2018-12-10 | 2
Way to store data from user
Periodic progress report
| Documentation | 2018-11-26 | 7 | 2018-12-03 | 1
Testing
| Deliver data for classification algorithm | 2018-12-10 | 14 | 2018-12-24 | 2
Research and code classification algorithm
| Documentation, Testing | 2018-12-10 | 7 | 2018-12-17 | 1
Final Phase | If user is not qualified for weight loss, let him choose if he still wants to follow healthy lifestyle and keep using recipes for everyday | 2019-01-07 | 7 | 2019-01-14 | 1
| Define 3 paces of weight loss and predict how the recipes are going to be selected | 2019-01-07 | 14 | 2019-01-21 | 2
| User's selection feature | 2019-01-07 | 7 | 2019-01-14 | 1
Documentation, Testing
| Deliver data for weight loss predictions | 2019-01-21 | 14 | 2019-02-04 | 2
Predictive modelling Feature for outputting predicted weight loss in time
Code algorithm
Code graphs and output to the user
| Output recipes to User FEATURE | 2019-02-04 | 7 | 2019-02-11 | 1
Possibility to print recipes to PDF
Testing, Documentation
| User day-to-day inputs recording and storing for outputting | 2019-02-11 | 7 | 2019-02-18 | 1
Enabling user to adjust the last input if wrong
Outputting to the user his progress and further predictions based on his inputs as graph
| Application warning once when desired weight was achieved | 2019-02-18 | 7 | 2019-02-25 | 1
Choice for user if he wants to continue healthy diet adjusted to his new needs
| Testing | 2019-02-22 | 30 | 2019-03-24 | 1
Documentation
| Lifecycle | 2019-02-25 | 30 | 2019-03-27 | 1
| Use Case Diagrams/Use Case Descriptions/Class diagrams | 2019-02-28 | 30 | 2019-04-05 | 4
Description how verification and validation were applied
Description of the use of tools to support the development process
Description of any research hypothesis
Bibliography
Lessons learnt log
Final Report